## Dashboard
Defect / Bug Register - HVAS + MUBS
Metric | Formula
Total Items | 14
Open | 6
In Progress | 1
Closed | 7
Critical/High Priority | 10

## Bug_Register
ID | Type | System | Module / Area | Severity | Priority | Description | Evidence / Source | Root Cause | Impact | Owner | Status | Date Reported | Target Fix Date | Resolution / Fix | Retest Evidence | Notes
QA-001 | Test Gap | HVAS | Automated tests | Medium | High | HVAS Python test files are placeholders and do not contain executable assertions. | Codebase audit: tests/test_detection_logic.py, test_storage_integration.py, test_video_ingestion.py | Tests were planned but not implemented in codebase. | Weakens automated QA evidence for HVAS. | <owner> | Open | <date> | <date> | Add pytest assertions or document manual testing evidence. | <path>
QA-002 | Security/Config Gap | Both | Environment templates | High | High | No .env.example or safe configuration template was found while sensitive configuration files exist. | Codebase audit environment/config findings | Configuration remained local/demo oriented. | Risk of secret exposure and weak handover reproducibility. | <owner> | Open | <date> | <date> | Create sanitised templates and redact screenshots/files. | <path>
QA-003 | Documentation Gap | HVAS | API documentation | Medium | Medium | OpenAPI/Postman documentation is incomplete compared with implemented routes. | Codebase audit API documentation section | Source routes exist but formal API spec is minimal. | Makes API evidence harder for assessors to verify. | <owner> | Open | <date> | <date> | Export or write final API collection/specification. | <path>
QA-004 | Test Evidence Gap | Both | Runtime evidence | High | High | Executed test logs and runtime screenshots are not present in repository evidence. | Codebase audit top missing materials | Static audit cannot prove final runtime behaviour. | Final system test report remains incomplete without screenshots/logs. | <owner> | Open | <date> | <date> | Capture screenshots/logs and link them in test report. | <path>
QA-005 | Security Limitation | HVAS | Prototype APIs | Medium | Medium | Several HVAS routes appear unauthenticated in the local prototype. | Codebase audit API/security notes | Prototype prioritised integration over production-grade security. | Must be documented as limitation or improved before real deployment. | <owner> | Open | <date> | <date> | Document limitation and consider API key/JWT protection. | <path>
QA-006 | Process Evidence Gap | Both | Formal QA records | Low | Medium | Code review, Fagan inspection and acceptance records were not found in repository. | Codebase audit QA section | Formal QA artefacts were not stored in code repository. | Portfolio QA evidence may appear incomplete. | <owner> | Open | <date> | <date> | Complete provided templates with real review/acceptance evidence. | <path>
QA-007 | Bug | HVAS | Stream Manager / task update | High | High | Updating a configured RTSP stream to enable multiple tasks could return HTTP 409 CONFLICT instead of applying the new task set. | User-reported browser error: Failed to load resource: the server responded with a status of 409 (CONFLICT) during multi-task update. | The task-update path can hit a runtime switching conflict while replacing handlers/executors, and the UI/server flow did not make the operation safely retryable for operators. | Operators may be blocked from running smoke/fire and parking-fence detection on the same RTSP stream. | HVAS Developer | In Progress | 2026-05-06 | 2026-05-08 | Make task replacement idempotent or surface a retry path, then confirm PUT /api/streams/<stream_id>/tasks returns 200 for combined task sets. | Pending final UI/Postman retest with parking_violation + smoke_flame on one stream. | Conversation defect; related code area: backend/api/stream_routes.py and backend/services/stream_manager.py.
QA-008 | Bug | HVAS | RTSP sampling / executor | High | High | A single stream-level sampling rate forced incompatible detection tasks to use the same cadence. | Discussion noted smoke/fire should not be sparsely sampled, parking fence should not run full-frame, and three full-frame RTSP streams could create queue/memory pressure. | Sampling interval was managed at stream/capture level instead of per detection task. | Multi-stream deployments could either miss smoke/fire signals or waste compute on parking detection, increasing latency and queue pressure. | HVAS Developer | Closed | 2026-05-06 | 2026-05-06 | Implemented task-level sampling intervals and exposed task_sample_intervals_sec metrics; parking defaults to 0.5s while smoke/flame can use a faster interval. | Runtime metrics show capture_sample_interval_sec and task_sample_intervals_sec per stream/task. | Related files: backend/main.py, backend/services/stream_runtime.py, backend/utils/frame_capture.py, frontend/src/views/StreamManager.vue.
QA-009 | Bug | HVAS | Parking fence GUI startup | Medium | High | Opening the parking-fence drawing GUI could take 7 to 8 seconds. | User reported long delay when configuring electronic fence before GUI appeared. | RTSP first-frame capture happened synchronously during GUI startup, blocking the Tk main thread while VideoCapture opened/read the stream. | Operators perceive the tool as frozen and may retry or abandon fence configuration. | HVAS Developer | Closed | 2026-05-06 | 2026-05-06 | Moved RTSP first-frame loading to an async worker queue and kept Tk UI updates on the main thread. | GUI script compiled successfully; user later confirmed the frame window could appear. | Related file: scripts/draw_fence_gui.py.
QA-010 | Bug | HVAS | Parking fence GUI frame preview | High | High | The parking-fence GUI could open without displaying the video frame. | User reported that the parking electronic-fence window opened but had no frame image. | The first frame was not reliably delivered/rendered after the RTSP loading path, and the preview needed explicit async handoff and canvas image retention. | Users could not draw accurate no-parking zones because the source scene was not visible. | HVAS Developer | Closed | 2026-05-06 | 2026-05-06 | Updated frame loading/render flow so the first available RTSP frame is passed to the GUI canvas safely. | User retest: frame image could pop up after the fix. | Related file: scripts/draw_fence_gui.py.
QA-011 | Bug | HVAS | Parking fence polygon drawing | Medium | High | After completing one polygon, starting a new drawing reused the existing polygon's first point, preventing two separated polygons. | User reported that clicking Start Drawing after one polygon caused the new polygon's first point to default to the old polygon start. | Completed polygon state and current drawing point state were not separated/reset cleanly. | Operators could not configure multiple separate no-parking zones for one camera. | HVAS Developer | Closed | 2026-05-06 | 2026-05-06 | Separated completed polygons from the current polygon, reset current points on Start Drawing, and saved nested polygon lists. | Simulated multi-polygon save passed; script compilation succeeded. | Related file: scripts/draw_fence_gui.py.
QA-012 | Bug | HVAS | Parking violation event generation | High | High | When three RTSP streams were running, parking-fence events were generated only once even though every sampled frame should have been a violation. | User reported one parking event despite test video and drawn no-parking area implying repeated violations on each sampled frame. | Dwell tracking behaved like a one-shot threshold trigger and did not continue emitting violations after the dwell threshold was reached. | Continuous illegal parking could be severely underreported in the event timeline. | HVAS Developer | Closed | 2026-05-06 | 2026-05-06 | Changed dwell tracking so after the dwell threshold is reached, every subsequent in-zone sampled frame can return a violation. | Retest pattern with threshold 3 produced [0,0,1,1,1,1,1]. | Related files: backend/services/dwell_tracker.py and backend/services/violation_detection.py.
QA-013 | Bug | HVAS | Parking violation duplicate reporting | High | High | The same video frame could be reported multiple times as separate parking-fence events. | User reported abnormal electronic-fence recognition where one frame was uploaded/reported repeatedly. | The parking event persistence path did not reserve an idempotency key for source_id + event_type + frame_index before upload/save. | Duplicate event cards inflate counts and make operator review unreliable. | HVAS Developer | Closed | 2026-05-06 | 2026-05-06 | Added a per-process recent-frame reservation key with a lock and TTL; release occurs if upload or database save fails. | Reservation test returned [True, False, True] for same-frame and different-frame cases. | Related file: backend/services/violation_detection.py.
QA-014 | Bug | HVAS | Events List detail view | Medium | Medium | Event cards could not be opened to inspect eventID and all available event attributes. | User requested clickable event cards that expose eventID and every obtainable property in the opened card. | Events List only presented summary card data and lacked a detail modal/fetch flow for /api/events/<event_id>. | Assessors and operators could not audit full event metadata from the UI. | HVAS Developer | Closed | 2026-05-06 | 2026-05-06 | Added clickable/keyboard-openable event cards, a detail modal, event detail fetch, nested JSON attribute display, and copy JSON support. | EventList.vue SFC parse check passed. | Related file: frontend/src/views/EventList.vue.

## Categories
Status | Severity | Priority | Type | System
Open | Low | Low | Bug | HVAS
In Progress | Medium | Medium | QA Gap | MUBS
Closed | High | High | Documentation Gap | Both
Deferred | Critical |  | Security/Config Gap | HVAS/MUBS
Not a Defect |  |  | Test Gap
Process Evidence Gap